## Slide 1
L8. THE MODELLING PROJECT
 Leif Gustafsson 211211
(File: L8_Modelling_Project.pptx)
The phases of a modelling project have a main direction but iterations back to earlier phases are often necessary!
Occam’s razor
MODELLING
- Conceptual model
- Choice of representation
- Model structure
- Parameterisation
- Time handling
- Stochastics
- Statistical output devices
- Model fitting
Purpose
PROBLEM DEFINITION
- Objective(s) (purpose)
- Systemus boundaries & details level
VALIDATION
PROBLEM SOLVING
RESULT EVALUATION
RESULT PRESENTATION
INFORMATION

## Slide 2: A systematic, general method of modelling
Study a delimited systemus of related components (where the whole is ‘more’ than the sum of its components).
Divide the project into well-defined consecutive phases.
Organize the study as a project:
- A project involves one study.
- It has a start and an end (not an ongoing activity).
- It is an organised form of work (including necessary
competence on subjects and methods).
Use or build a model based on knowledge.
To do what is necessary.
Main ideas:
To do it in a proper and efficient order.
Validated the model, evaluate is usefulness & present the results.
Notes: 2

## Slide 3
The phases of a modelling project
Purpose
VII. INFORMATION
PROBLEM AWARENESS
I. PROBLEM DEFINITION
II. MODELLING
III. VALIDATION
IV. PROBLEM SOLVING
V. RESULT EVALUATION
VI. RESULT PRESENTATION
Notes: 3

## Slide 4
Information: (knowledge & data) needed throughout the project.
Problem awareness: Just a starting point. A first mental model.
Result presentation: ”Selling” your work!
Result evaluation: Interpret and evaluate the results. Have you
solved the problem (according to purpose)? Is the solution useful?
Problem solving: Analyses based on experiments with the model.
Validation: Test of model (trustworthy).
Modelling: Choice of model type. Model building. Fitting the model
to the system under study. Etc.
Problem definition: A) Formulation of purpose in operative terms.
B) Definition of the systemus (boundaries & level of aggregation).
The work is usually iterative. The modelling gives you new insights - then go back and refine when appropriate!
Notes: 4

## Slide 5
PROBLEM AWARENESS
(Astronaut on Apollo 13 when a
fuel cell had exploded.)
Huston, we have a problem!
A project often starts with a fuzzy experience of a problem or an idea to understand, make or improve something.
Notes: 5

## Slide 6
I. PROBLEM DEFINITION
Purpose
  A. Specifying the purpose (as clear and operational as possible)
To structure and formalise the problem:
”The most important thing is not to find the right answer
- it is to formulate the right questions!”
Solving a problem depends very much on how clear and
concrete a purpose is formulated!
  B1. Boundaries of the studied system
  B2. Specifying the level of details
The problem definition has two parts:
SYSTEMUS
B. Defining the system under study
The boundaries & detail level must be consistent with the purpose!
Notes: 6

## Slide 7
IA. The purpose – your guiding star
Would you tell me, please, which way I ought to go from here?
That depends on where you want to get to, said the Cat.
I don’t much care where, said Alice.
Then it doesn’t matter which way you go, said the Cat.
(Alice in Wonderland by Lewis Carroll, 1865. Public Domain)
Purpose

## Slide 8: Defining the purpose of the project
Some typical purposes ( objectives):
o Answer a question:
– How many accidents will a speed limit reduce? – Is a certain exposure dangerous?
– Is this intervention cost-efficient? – Which persons are at risk? – What treatment is best?
o Finding the cause of a problem:
– What causes this disease? – Why does this intervention give such a small effect?
o Finding a technique to handle a problem:
– Will HPV testing find cases that cytological screening misses?
o Optimisation (with or without restrictions):
– At what ages should mass screening be performed to minimize death in a specific cancer?
o Satisfaction (Finding a solution that has certain qualities, but not necessarily
the optimal one.):
– What is required to give 90% of the population a healthy life to at least age 75?
o Prediction:
– What will the effects of changing to electric vehicles be?
– How will the economy develop over the next decade?
o Understand the system under study:
e.g. inflation, epidemic, extinction of species …
Notes: 7

## Slide 9
IB1. Systemus boundaries
SYSTEMUS
ENVIRONMENT
(the rest of the universe)
Boundaries of the studied systemus
The solution depends on the problem definition!
Be aware that boundaries imply sub-optimisation! (Every solution is a sub-optimisation from a viewpoint of a higher hierarchical level.)
Example: You study a medical lab (= the systemus) and find an optimal use of a certain resource. But if you widen the boundaries to the whole hospital you should perhaps put the resources on e.g. surgery. And if you widen it to the whole society you should have used them on e.g. safer roads. And so on …
Purpose
Occam’s razor
What parts of reality to include or exclude?

## Slide 10
1B2. Level of details
SYSTEMUS
Subsystems
Including details will cost:
More data to be collected
More model fitting
More validation work
Increased risk of errors
Harder to comprehend, interpret and understand the results
More complicated result presentation
Have a very good reason to make a model more complex!!!
Purpose
What details do I need?
(The purpose decides what details are necessary to get
a realistic model.)
Occam’s razor: Don’t incorporate a concept if it is not necessary! Always strive to make the model as simple as possible!
(William Occam 1290-1349.)

## Slide 11
TO ORGANIZE THE PROJECT
During or after the problem definition, it is often time to organize the work in the form of a project.
o Participants:
- Field experts: (Medicine, economy, administration of a hospital, …)
- Methodological experts: (Modelling & simulation, Statistics, …)
Possibly, you should make a pilot study before starting a full scale project.
o What information exists or can be obtained?
o Project resources: (Persons, time, economy, knowledge, software, ...)
o Project time schedule.
o How to perform the work. (Who will do what? Software? …)
Notes: 8

## Slide 12
The need for a ‘common language’ in the project
Modelling issues, e.g.
Statistics
Modelling and simulation
Analysis
Field issues, e.g.
Researchers
Study design
Register handling
Etc.
Need for a ‘common language’
- e.g. System Dynamics*
* System Dynamics to describe the systemus in terms of stocks and flows.
RESULTS
Executable
MODEL
Conceptual
MODEL
SYSTEM
under study

## Slide 13
II. MODELLING
A model is a simplified representation of the system under study.
System, purpose and technique affect the model.
A model is never true or complete, but it can be better or worse (useful or not) for a given purpose.
Choice of model type
If possible, aim at a quantitative description. Depending on
complexity, knowledge etc. there is a hierarchy of techniques:
Simulation models (Micro or macro?)
Mathematics
Statistics
Quantitative models
Schemes, Graphs, Drawings, Blueprints, etc.
Verbal descriptions.
Experience, feelings and other mental models.
Notes: 9

## Slide 14
According to purpose, you want to build a model that (is):
  Static/Dynamic
  Deterministic/Stochastic
  Linear/Non-linear
  Micro/Macro representation
  Only describes change over time t/Also change over x, y & z
  Describes the process/Only relates inputs to outputs
  …
What type of model to use?

## Slide 15
o Different types of randomness: (e.g. realised in stocks (initial values), flows, parameters and/or signals.)
o Initial conditions: (e.g. S(0)=1000, I(0)=7, R(0)=23)
o Data description: Quantitative values. Model structure and
algorithms specify what data are needed. (e.g. c=0.0003, T=4)
o Process description: Model algorithms (e.g. F1=cSI, F2=I/T)
Steps in the modelling work
o Structural description: Define components and the structural relations between them (with Stages, Flows, Links etc.).
S
I
R
F2
F1
StochSD example:
Notes: 10

## Slide 16: Two main types of models
White-box model: Describing the entire systemus. (Structure and relations based on Laws of nature). Works well for technical systemus.
Identification (Test reasonable model structures. Then trim the parameters for each candidate to obtain a model, which as well as possible behaves like the systemus.) Often necessary for studies of economical, biological, medical, sociological, etc. systems.
SYSTEMUS
White-box MODEL
Describe the entire systemus
Black-box MODEL
Describe only input-output relations
There are also Grey-box models, which are partly white (e.g. overall structure) but complemented by black-box features.
Black-box model: Describes only the relations between inputs and outputs of the system under study. Here we need only a model, which reproduces the i-o relations.

## Slide 17
Identification (Fitting a model to the systemus)
SYSTEMUS
MODEL
Same input
ys
ym
e = ys-ym
+
-
Parameter values of x1 .. xn
The difference between ys and ym is calculated. ‘Tune’ the model parameters so that the difference e=ys – ym over time becomes as small as possible.
To get a quadratic measure: .
Parameter estimation
For each candidate structure, tune the parameters so that the model behaves like the systemus as much as possible.
Identification is a technique to find the best model (structure, relations, parameter values) among your candidate models.
Notes: 12

## Slide 18
III. VALIDATION
Validation requires a huge amount of work if the model is complex. (Never make the model more complex than necessary.)
Is the model valid (trustworthy) according to the purpose?
DATA
SYSTEMUS
Computer program
RESULTS
MODEL
D. TOTAL VALIDATION
A. Data validation
B. Validation of hypotheses
C. Technical validation
(verification)
18
Notes: 14

## Slide 19: Only validate what is important for your purpose!
Example: If your purpose is to calculate the number of Susceptibles and Infectious during an epidemic – only what considerably affects these numbers have to be validated.
However, you may model the Susceptibles as blue triangles and the Infectious as purple circles ( - unless the purpose is to describe their colours and shapes)!
WARNING: Never use a model for a purpose or conditions for which it is not intended, fitted and validated. (This is a very common mistake!)

## Slide 20
Different parts of the validation work
A) Data validation
GIGO = Garbage In - Garbage Out!
Are data sufficiently accurate? (Use sensitivity analysis!)
Systematic errors (bias): old figures, bad calibration, leading
questions, selection bias, etc.
- Random errors: (Small samples, limited accuracy).
Statistical distributions are sometimes required to model: Arrival
times, Service times, Sojourn time in a stage, Varying external
conditions, etc. Are these statistical distributions accurate?
Notes: 15

## Slide 21: B) Validation of hypotheses
The hypotheses about structure and functions must be realistic.
But also left out parts or relations may be important. [E.g. should you include an E-stage (exposed but not yet infectious) into the SIR model?]
How good is the knowledge about the systemus?
(Rather exact or coarse guesses.)
How much does a hypothesis affect the model behaviour?
Sensitivity analysis gives the answer. (How will a small change in
c or T affect the SIR epidemic?)
Is the aggregation level OK? Do we need all the details? Must we
refine some parts (e.g. stratify for sex, age or risk behaviour)?

## Slide 22
C) Technical validation (Verification)
Test the program logics.
Stepwise execution of simple cases.
Test of program for cases where the answers are known.
Log-lists, animations etc. are useful.
Is the technical realisation of the model correctly done?
- Programming errors.
- Logical errors.
- Typing errors.
Notes: 16

## Slide 23: D) Total validation (also called result validation)
Refers to the behaviour of the model as a whole.
Does the model behave like the real systemus (with respect to the purpose)?
NOTE! Total validation requires “new” (independent) data - not used in the model fitting process!
Example: Assume you have fitted a model to the influenza outbreak in 2018. It is then not meaningful to validate that the model fits these 2018 data already used for fitting.
Total validation is the crucial test. Partial validations, A, B & C above, are important to find the errors or weak points in the model.

## Slide 24: Total validation - continued
Data to compare:
- averages
- variations
- max or min values
- distributions
time series
etc.
Comparisons may be based on:
- Similarity in behaviour
- Statistical tests
- Subjective judgement by an expert

## Slide 25
IV. PROBLEM SOLVING
The analysis depends on the purpose and the model type chosen.
Study what happens if …
Predict the consequences of …
Find the optimal use of some measures
Calculate the costs of …
Find the relation between dose and response
- Comparing different strategies
- ...
Often large computations are necessary to understand the results from a simulation model.
Then limiting the number of experiments is often necessary. (‘Experimental Design’ is a is a way to reduce the number of experiments – see L7.)
Analysis of the model and its behaviour, by e.g. simulation (experiments on the model ).
Notes: 17

## Slide 26
V. RESULT EVALUATION
Assessment of the results. What do the results say? Do they agree with reality. Are they useful?
Interpretation of the results also includes:
- Boundaries of the systemus
- Hypotheses used
- Results from sensitivity analysis
- Insights from the validation
Subjective evaluation of the results. Is the solution reasonable? Can omitted factors affect the conclusions?
Pragmatic evaluation of the results.
Is the solution practical and economically, ethically and politically possible?
Compare results and purpose. Have you solved the problem?
Notes: 18

## Slide 27
VI. RESULT PRESENTATION
Crucial with a good and structured presentations.
Use figures and graphs.
(A figure says more than a thousand words.)
Eliminate irrelevant information.
(Focus on your purpose!)
Boundaries, assumptions,
simplifications, insecurities
should be clearly stated.
27
Notes: 19

## Slide 28
VII. INFORMATION
Different kinds of information are needed during a project:
Knowledge
Data
From literature
Expert’s opinions
Experience/insight
A pilot study
Be clear of what data you really need! Don’t try to collect everything!!!
No modelling of a systemus can be done without information about the systemus and its behaviour. Also the effects from the environment can be important to understand.
Notes: 13

## Slide 29: You need information for:
Problem definition: Experts, literature, some data collection can
be a good start.
Problem solving: Sometimes you need input data (time series,
tables, parameter values) to represent interesting alternatives to
be analysed.
Validation: Test whether the model behaves like the systemus.
Note: You need new, independent data here! That the model works
well for the case you used to fit the model is trivial and doesn’t prove
anything.
Modelling: Structure, relations, external inputs (e.g. weather,
arriving customers), parameter values. Fitting the model to the
studied system.
Result evaluation: To judge usefulness of the results from a wider
perspective you may need additional information (e.g. about the
environment to the system under study, side effects, economical,
ethical or juridical aspects).

## Slide 30: Don’t over-interpret the data
We may require more information. More points. How accurate are the data?
Information (data) is never exact or complete.
All higher degree polynomials can also go through the three
points – but behave very differently in between!
”We want to model the system under study – not the measurement errors!”
y
x
*
*
*
Example: Say you have three data points like in the figure.
How to model this information?
a) y=a (constant)
b) y=a + b*x
c) y = a + b*x + c*x2 (Perfect match or over-parameterization?)
(N point can always be perfectly matched by a polynomial of degree N-1. But if the
data are not perfect, this might still be a bad model!)

## Slide 31: VIII. ITERATIONS
In a typical project you learn during the work, get new information and understand that structure, relations or parameter values used are not the best.
Then you have to revisit earlier stages.
In a serious modelling project, iterations are frequent.

## Slide 32
IX. COMMON REASONS FOR A FAILURE
…
Important aspects are not considered. (technical, medical, economical, practical, juridical, ethical …)
Bad project management. (E.g. you did not follow the
project phases for running a modelling project.)
Improper choice of model type.
Insufficient communication between field experts
and modellers. Perhaps no common language!
Inadequate or bad information/data about the
systemus.
Notes: 21

## Slide 33: References
Fishman, G.S. Principles of Discrete Event Simulation. John Wiley & Sons, NY, 1978.
Kelton, D.W., Sadowski, R.P. and Sadowski, D.A. Simulation with Arena. WCB/McGraw-Hill, 1998. (Arena is a DES language. However, Chapter 1: What is Simulation? and Chapter 2: Fundamental Simulation Concepts – including 2.7 Overview of a Simulation Study are of general interest.)
Law AM and Kelton WD. Simulation Modelling and Analysis, 2d ed. McGraw-Hill, New York, 1991.
Ljung L. System Identification: Theory for the User, Prentice-Hall, Inc., NJ, 1999.
Randers J. editor. Elements of the System Dynamics Method. The MIT Press, Ma, 1980.

## Slide 34: End L8